## Sheet1
SL NO. | TICKET - ID | TICKET - CATEGORY | TICKET - SUMMARY | ASSIGNED TO | COMMENTS
1 | GC - 690 | Bug | Is Title of a Solution - a mandatory field ? | Development | Converted to a Bug as per Lucas' comments in Jira .
2 | GC - 700 | Bug | Unable to create a new issue from Django Admin . | Development
3 | GC - 701 | Bug | Unable to View/Update Issue details from GC UI . | Development
4 | GC - 718 | Request | How to find the Group ID of a Group ? | Product | Jira - Status "In Review" and comments updated , after discussion with Lucas .
5 | GC - 719 | Request | What is the significance of "Cancel Project" ? | Product | Jira - Status "In Review" and comments updated , after discussion with Lucas .
6 | GC - 720 | Bug | "Create Token" API Request (POST) returns Response Code 200 instead of 201 . | Development
7 | GC - 721 | Bug | "Delete Solution" API Request (Delete) returns Response Code 200 instead of 204 . | Development
8 | GC - 722 | Bug | Not getting proper Response from the API - "Retrieve Active Session(Get)" . | Development
9 | GC - 723 | Bug | The CLI command for Session - "List for project & export to CSV file" is not working as expected | Development
10 | GC - 725 | Request | How does the "Suggest Solution" API work for Issues from Same/Different Project ? | Product | Jira - Status "In Review" and comments updated , after discussion with Lucas .
11 | GC - 726 | Request | Request for proper Test Data regarding the API Test Execution . | Development
12 | GC - 728 | Bug | Unable to invite a Member to a Project using the "Import File" feature . | Development
13 | GC - 729 | Request | Unable to see "Organization - Slug" in the GC - UI . | Product | Jira - Status "Done" .
14 | GC - 730 | Bug | Unable to save the new value of "Organization - Slug" after modifying it . | Development
15 | GC - 732 | Bug | Unable to delete a Project using the "Remove Project" - API . | Development
16 | GC - 740 | Bug | Nomenclature of a Project's status is different in Django Admin vs IMERIT-CLI . | Development
17 | GC - 741 | Bug | Fields - 'Item Count' and 'Progress' are a part of CLI Response but not a part of the "Create Project" API . | Development
18 | GC - 742 | Request | What is the significance of "Project Status = Draft" ? | Product | Jira - Status "Archieved" .
19 | GC - 743 | Request | What is the significance of 'Submit Project' in IMERIT-CLI ? | Product | Jira - Status "Archieved" .
20 | GC - 744 | Bug | Is 'External Platform ID' a mandatory field while creating a Project ? | Development
21 | GC - 745 | Bug | Unable to save the Project's Status after changing it in Django Admin . | Product | Jira - Status "Archieved" .
22 | GC - 782 | Bug | User is not getting Email notification about getting Membership invitation from Project / Organization from IMERIT - CLI | Development
23 | GC - 783 | Bug | In IMERIT-CLI - "List of Issues" ; Reporter = "georges" instead of "georges@imerit.net" (Django) . | Development
24 | GC - 784 | Request | How many max Members can be invited to a Organization/Project in a batch i.e. how many rows can 1 csv handle ? | Product | Jira - Status "Done" .
25 | GC - 811 | Request | Unable to prepare a Quicksight Dashboard after creating a Athena Dataset due to Permission issues regarding the S3 Bucket | Development